## SUMMARY
VistA Evolved — Admin Panel Definitive Audit
All 18 Pages · All M Routines · All Server Routes
TOTAL ISSUES | 411
CRITICAL | 13 | Data corruption, data loss, broken core flows
HIGH | 132 | Key verification, non-functional UI, security gaps
MEDIUM | 165 | UX, validation, performance, features
LOW | 101 | Enhancements, polish, accessibility
EXECUTION PHASES:
Phase 1: Data Loss (A) | 22 | Wizard fields that never reach VistA — URGENT
Phase 2: Corruption (B) | 48 | SSN bugs + all 43 key verifications — URGENT
Phase 3: Broken Flows (C) | 13 | Edit mode, status, clone — HIGH
Phase 4: Non-Functional (D) | 7 | Facility selector, bell, CSV — HIGH
Phase 5: Terminal + UX (E+F) | 43 | Missing features + design — MEDIUM
Phase 6: Security (G) | 14 | Rate limiting, XSS, SSN masking — MEDIUM
Phase 7: Ch2+Ch3 | 38 | Roles, permissions, security config — MEDIUM
Phase 8: Other Pages | 42 | All remaining admin pages — LOW-MEDIUM
Phase 9: Global + Polish | 70 | Cross-cutting, workflow, API — LOW

## 01-DataLoss
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
A001 | CRITICAL | DataLoss-Create | StaffForm | Create: permissions (VistA Keys) never saved | Zero keys written. Physician can't sign orders. | Loop body.permissions, call ZVE KEY ASSIGN for each. | Create user → M: check Keys
A002 | CRITICAL | DataLoss-Create | StaffForm | Create: email (VistA .151) never saved | Email collected but never saved. | Add email:".151" to EXTRA_MAP. | Create user → M: check .151
A003 | CRITICAL | DataLoss-Create | StaffForm | Create: phone (VistA .132) never saved | Phone collected but never saved. | Add phone:".132" to EXTRA_MAP. | Create user → M: check .132
A004 | CRITICAL | DataLoss-Create | StaffForm | Create: npi (VistA 41.99) never saved | NPI not saved. Can't bill. | Add npi:"41.99" to EXTRA_MAP. | Create user → M: check 41.99
A005 | CRITICAL | DataLoss-Create | StaffForm | Create: dea (VistA 53.2) never saved | DEA not saved. Can't prescribe CS. | Add dea:"53.2" to EXTRA_MAP. | Create user → M: check 53.2
A006 | CRITICAL | DataLoss-Create | StaffForm | Create: providerType (VistA 53.5) never saved | Provider type not saved. | Add providerType:"53.5" to EXTRA_MAP. | Create user → M: check 53.5
A007 | CRITICAL | DataLoss-Create | StaffForm | Create: division (VistA 200.02) never saved | Division not assigned. No facility. | Call ZVE DIVISION ASSIGN after creation. | Create user → M: check 200.02
A008 | HIGH | DataLoss-Create | StaffForm | Create: additionalDivisions (VistA 200.02) never saved | Extra divisions not assigned. | Loop additionalLocations, call ZVE DIVISION ASSIGN. | Create user → M: check 200.02
A009 | HIGH | DataLoss-Create | StaffForm | Create: language (VistA 200.07) never saved | Language not saved. | DDR FILER for field 200.07. | Create user → M: check 200.07
A010 | HIGH | DataLoss-Create | StaffForm | Create: vcNeverExpires (VistA 9.5) never saved | VC Never Expires flag not set. | DDR FILER for field 9.5. | Create user → M: check 9.5
A011 | HIGH | DataLoss-Create | StaffForm | Create: restrictPatient (VistA 101.01) never saved | Restrict patient not set. | DDR FILER for field 101.01. | Create user → M: check 101.01
A012 | HIGH | DataLoss-Create | StaffForm | Create: employeeId (VistA Custom) never saved | Employee ID not saved. | Create ZVE extension field. | Create user → M: check Custom
A013 | HIGH | DataLoss-Create | StaffForm | Create: sigBlockName (VistA 20.3) never saved | Sig block not saved. | DDR FILER for field 20.3. | Create user → M: check 20.3
A014 | HIGH | DataLoss-Create | StaffForm | Create: cosigner (VistA 53.42) never saved | Cosigner not saved. | DDR FILER for field 53.42. | Create user → M: check 53.42
A015 | HIGH | DataLoss-Create | StaffForm | Create: requiresCosign (VistA 53.42+) never saved | Cosign flag not saved. | Map to VistA field. | Create user → M: check 53.42+
A016 | HIGH | DataLoss-Create | StaffForm | Create: authToWriteMeds (VistA 53.11) never saved | Auth meds not saved. | DDR FILER for field 53.11. | Create user → M: check 53.11
A017 | HIGH | DataLoss-Create | StaffForm | Create: controlledSchedules (VistA 55) never saved | CS schedules not saved. | DDR FILER for field 55. | Create user → M: check 55
A018 | HIGH | DataLoss-Create | StaffForm | Create: filemanAccess (VistA 3) never saved | FM access not saved. | DDR FILER for field 3. | Create user → M: check 3
A019 | MEDIUM | DataLoss-Create | StaffForm | Create: displayName (VistA N/A) never saved | Display name not persisted. | Store in ZVE extension or derive. | Create user → M: check N/A
A020 | MEDIUM | DataLoss-Create | StaffForm | Create: deaExpiration (VistA Custom) never saved | DEA expiration not saved. | Map to field or extension. | Create user → M: check Custom
A021 | MEDIUM | DataLoss-Create | StaffForm | Create: roleAssignment (VistA Custom) never saved | Role not recorded persistently. | Store in ZVE extension. | Create user → M: check Custom
A022 | MEDIUM | DataLoss-Create | StaffForm | Create: secondaryFeatures (VistA Menu) never saved | Secondary features not saved. | Map to menu options. | Create user → M: check Menu

## 02-Corruption
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
B001 | CRITICAL | Corruption | ZVEUSMG.m | DEACT writes date to SSN field (field 9) | S FDA(200,TDUZ_",",9)=DT — field 9=SSN not termination date | Set DISUSER ($P(^VA(200,+TDUZ,7),U,1)=1) + field 9.2=DT | M: SSN unchanged, DISUSER=1
B002 | CRITICAL | Corruption | ZVEUSMG.m | REACT deletes SSN field | S FDA(200,TDUZ_",",9)="@" — deletes SSN | Clear DISUSER + field 9.2="@" | M: SSN intact after reactivate
B003 | CRITICAL | Corruption | server.mjs | Key sanitizer strips dashes — ORCL-SIGN-NOTES→ORCLSIGNNOTES | replace(/[^A-Z0-9 ]/g,"") removes dashes | Change to /[^A-Z0-9 \-]/g | Assign ORCL-SIGN-NOTES → no error
B004 | HIGH | Corruption | ZVEUSMG.m | Existing SSNs may be corrupted by prior DEACT calls | Any user previously deactivated has date in SSN field | Run SSN scan script at M prompt | Report corrupted SSNs
B005 | HIGH | Corruption | RoleTemplates | DG REGISTRATION may not be a real VistA key | Used in Registration Clerk role | Verify at M: W $O(^DIC(19.1,"B","DG REGISTRATION",0)) | Key exists or removed
B006 | HIGH | KeyVerify | RoleTemplates | Verify key "PROVIDER" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PROVIDER",0)) | Returns >0
B007 | HIGH | KeyVerify | RoleTemplates | Verify key "ORES" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","ORES",0)) | Returns >0
B008 | HIGH | KeyVerify | RoleTemplates | Verify key "OR CPRS GUI CHART" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","OR CPRS GUI CHART",0)) | Returns >0
B009 | HIGH | KeyVerify | RoleTemplates | Verify key "ORCL-SIGN-NOTES" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","ORCL-SIGN-NOTES",0)) | Returns >0
B010 | HIGH | KeyVerify | RoleTemplates | Verify key "ORCL-PAT-RECS" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","ORCL-PAT-RECS",0)) | Returns >0
B011 | HIGH | KeyVerify | RoleTemplates | Verify key "GMRA ALLERGY VERIFY" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","GMRA ALLERGY VERIFY",0)) | Returns >0
B012 | HIGH | KeyVerify | RoleTemplates | Verify key "ORELSE" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","ORELSE",0)) | Returns >0
B013 | HIGH | KeyVerify | RoleTemplates | Verify key "PSB NURSE" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSB NURSE",0)) | Returns >0
B014 | HIGH | KeyVerify | RoleTemplates | Verify key "OREMAS" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","OREMAS",0)) | Returns >0
B015 | HIGH | KeyVerify | RoleTemplates | Verify key "PSORPH" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSORPH",0)) | Returns >0
B016 | HIGH | KeyVerify | RoleTemplates | Verify key "PSJ PHARMACIST" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSJ PHARMACIST",0)) | Returns >0
B017 | HIGH | KeyVerify | RoleTemplates | Verify key "PSO MANAGER" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSO MANAGER",0)) | Returns >0
B018 | HIGH | KeyVerify | RoleTemplates | Verify key "PSOPHARMACIST" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSOPHARMACIST",0)) | Returns >0
B019 | HIGH | KeyVerify | RoleTemplates | Verify key "PSOINTERFACE" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSOINTERFACE",0)) | Returns >0
B020 | HIGH | KeyVerify | RoleTemplates | Verify key "PSD PHARMACIST" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSD PHARMACIST",0)) | Returns >0
B021 | HIGH | KeyVerify | RoleTemplates | Verify key "PSDRPH" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","PSDRPH",0)) | Returns >0
B022 | HIGH | KeyVerify | RoleTemplates | Verify key "LRLAB" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","LRLAB",0)) | Returns >0
B023 | HIGH | KeyVerify | RoleTemplates | Verify key "LRVERIFY" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","LRVERIFY",0)) | Returns >0
B024 | HIGH | KeyVerify | RoleTemplates | Verify key "LRSUPER" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","LRSUPER",0)) | Returns >0
B025 | HIGH | KeyVerify | RoleTemplates | Verify key "LRMGR" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","LRMGR",0)) | Returns >0
B026 | HIGH | KeyVerify | RoleTemplates | Verify key "LRCAP" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","LRCAP",0)) | Returns >0
B027 | HIGH | KeyVerify | RoleTemplates | Verify key "SD SCHEDULING" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","SD SCHEDULING",0)) | Returns >0
B028 | HIGH | KeyVerify | RoleTemplates | Verify key "SDCLINICAL" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","SDCLINICAL",0)) | Returns >0
B029 | HIGH | KeyVerify | RoleTemplates | Verify key "SD SUPERVISOR" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","SD SUPERVISOR",0)) | Returns >0
B030 | HIGH | KeyVerify | RoleTemplates | Verify key "SDMGR" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","SDMGR",0)) | Returns >0
B031 | HIGH | KeyVerify | RoleTemplates | Verify key "DG REGISTER" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG REGISTER",0)) | Returns >0
B032 | HIGH | KeyVerify | RoleTemplates | Verify key "DG REGISTRATION" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG REGISTRATION",0)) | Returns >0
B033 | HIGH | KeyVerify | RoleTemplates | Verify key "DG ADMIT" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG ADMIT",0)) | Returns >0
B034 | HIGH | KeyVerify | RoleTemplates | Verify key "DG DISCHARGE" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG DISCHARGE",0)) | Returns >0
B035 | HIGH | KeyVerify | RoleTemplates | Verify key "DG TRANSFER" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG TRANSFER",0)) | Returns >0
B036 | HIGH | KeyVerify | RoleTemplates | Verify key "DG MENU" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG MENU",0)) | Returns >0
B037 | HIGH | KeyVerify | RoleTemplates | Verify key "DG SUPERVISOR" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG SUPERVISOR",0)) | Returns >0
B038 | HIGH | KeyVerify | RoleTemplates | Verify key "DG SENSITIVITY" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DG SENSITIVITY",0)) | Returns >0
B039 | HIGH | KeyVerify | RoleTemplates | Verify key "DGMEANS TEST" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","DGMEANS TEST",0)) | Returns >0
B040 | HIGH | KeyVerify | RoleTemplates | Verify key "RA TECHNOLOGIST" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","RA TECHNOLOGIST",0)) | Returns >0
B041 | HIGH | KeyVerify | RoleTemplates | Verify key "RA ALLOC" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","RA ALLOC",0)) | Returns >0
B042 | HIGH | KeyVerify | RoleTemplates | Verify key "MAG SYSTEM" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","MAG SYSTEM",0)) | Returns >0
B043 | HIGH | KeyVerify | RoleTemplates | Verify key "MAG CAPTURE" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","MAG CAPTURE",0)) | Returns >0
B044 | HIGH | KeyVerify | RoleTemplates | Verify key "XUMGR" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","XUMGR",0)) | Returns >0
B045 | HIGH | KeyVerify | RoleTemplates | Verify key "XUPROG" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","XUPROG",0)) | Returns >0
B046 | HIGH | KeyVerify | RoleTemplates | Verify key "XUPROGMODE" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","XUPROGMODE",0)) | Returns >0
B047 | HIGH | KeyVerify | RoleTemplates | Verify key "XUAUDITING" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","XUAUDITING",0)) | Returns >0
B048 | HIGH | KeyVerify | RoleTemplates | Verify key "IBFIN" exists in VistA 19.1 | If not in ^DIC(19.1,"B"), assignment silently fails | M: W $O(^DIC(19.1,"B","IBFIN",0)) | Returns >0

## 03-BrokenFlows
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
C001 | CRITICAL | BrokenFlow | StaffForm | Edit mode broken — server rejects bulk payload | PUT expects {field,value} but wizard sends {name,email,...} | Wizard must send individual field updates | Edit phone → saves
C002 | HIGH | BrokenFlow | server.mjs | Edit can't save language (not in ALLOW list) | Field 200.07 missing from ALLOW map | Add to ALLOW + ZVE_FIELD_MAP | Edit language → saves
C003 | HIGH | BrokenFlow | server.mjs | Edit can't save division | Sub-file needs ZVE DIVISION ASSIGN | Use RPC instead of DDR FILER | Edit division → saves
C004 | HIGH | BrokenFlow | server.mjs | Edit can't save restrict patient | Field 101.01 missing | Add to ALLOW | Edit → saves
C005 | HIGH | BrokenFlow | server.mjs | Edit can't save VC never expires | Field 9.5 missing | Add to ALLOW | Edit → saves
C006 | HIGH | BrokenFlow | ZVEUSMG.m | Deactivation reason not written to VistA 9.4 | DEACT doesn't accept REASON param | Add REASON param, write field 9.4 | M: W $$GET1^DIQ(200,DUZ_",",9.4)
C007 | HIGH | BrokenFlow | ZVEADMIN.m | Status inconsistency: list vs detail | LIST2 checks DISUSER+TERMDT, DETAIL checks only DISUSER | Add TERMDT check to DETAIL | Terminated user shows same in both
C008 | HIGH | BrokenFlow | ZVEADMIN.m | Locked status never returned by LIST2 | Never checks ^XUSEC("LOCKED") | Add locked check to LIST2 | Locked user shows LOCKED
C009 | HIGH | BrokenFlow | ZVECTX2.m | Clone User RPC may not be registered | ZVE USER CLONE not in ADDRPC list? | Verify and add if missing | Clone works end-to-end
C010 | HIGH | BrokenFlow | SecurityAuth | 2P auth may queue changes forever | No timeout/escalation on pending 2P requests | Add timeout and admin notification | 2P changes don't hang indefinitely
C011 | MEDIUM | BrokenFlow | StaffForm | Name rename not handled in edit mode | Wizard doesn't call rename route for .01 changes | Call PUT /users/:duz/rename if name changed | Edit name → renames in VistA
C012 | MEDIUM | BrokenFlow | StaffDirectory | Provider field save: person class sub-file may fail | 200.05 is sub-file, DDR FILER may reject | Test and fix with direct global or dedicated RPC | Edit person class → saves
C013 | MEDIUM | BrokenFlow | StaffDirectory | Detail panel provider type reads wrong index | Server reads detail[14] (PCLASS 53.1) but labels it providerType | Verify index mapping matches M routine output order | Correct provider type shown

## 04-NonFunctional
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
D001 | HIGH | NonFunc | SystemBar | Facility selector does nothing | activeSite local state, never used | Wire via FacilityContext or remove | Click facility → list filters
D002 | HIGH | NonFunc | SystemBar | Notifications bell is dummy | No onClick, no badge, no dropdown | Connect to MailMan or remove | Bell works or removed
D003 | HIGH | NonFunc | NavRail | 8 nav items are placeholders | Scheduling→Analytics = WorkspacePlaceholder | Add "Coming Soon" or dim | Clearly marked as upcoming
D004 | MEDIUM | NonFunc | StaffDirectory | CSV export ignores active filters | Exports staffList not filtered | Change to filtered.map(...) | Export matches current view
D005 | MEDIUM | NonFunc | StaffDirectory | No empty state when filters return 0 | Table blank with no message | Add helpful empty state message | 0 results → message shown
D006 | MEDIUM | NonFunc | StaffDirectory | E-sig clear button shows when not set | Shows regardless of esigStatus | Show only when active | Not-set → text instead of button
D007 | MEDIUM | NonFunc | StaffDirectory | EditableDetailField swallows errors | catch block empty | Add inline error display | Error → red message shown

## 05-TerminalGaps
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
E001 | HIGH | TermGap | LoginPage | No self-service password reset | No Forgot Password link | Build email-based reset flow | Forgot → email → new password
E002 | HIGH | TermGap | ZVEUSMG.m | No forced password change on first login | CRED doesn't set field 11.2 | Set 11.2 to past date in CRED | First login forces change
E003 | HIGH | TermGap | StaffForm | No OE/RR List (CPRS team) assignment | Field 200.0001 not in wizard | Add team selector | Team assigned on create
E004 | HIGH | TermGap | StaffDirectory | CPRS Tab Access is read-only | Can view but not edit File 200.03 | Add toggle switches, save via DDR | Toggle tab → saves
E005 | MEDIUM | TermGap | StaffDirectory | Proxy user not editable | Field 203.1 shown but can't change | Add EditableDetailField | Set proxy → saves
E006 | MEDIUM | TermGap | StaffDirectory | No user activity summary | Missing: sign-on count, last option, creation date | Read from sign-on log | Detail shows activity
E007 | MEDIUM | TermGap | StaffDirectory | No password expiration date display | Not calculated from 11.2 + system param | Calculate and show in detail | Shows "Expires: Jul 15"
E008 | MEDIUM | TermGap | StaffDirectory | No sig block editing in detail | Fields 20.2/20.3 returned but not editable | Add EditableDetailField | Edit sig block → saves
E009 | MEDIUM | TermGap | server.mjs | No FM access level setting | Field 3 not in ALLOW | Add to ALLOW | Set FM access → saves
E010 | MEDIUM | TermGap | StaffForm | No Primary Menu in wizard UI | Field 201 in EXTRA_MAP but no selector | Add menu selector defaulting to CPRS | Create → menu set
E011 | MEDIUM | TermGap | StaffForm | No degree/suffix field | Field 10.6 not in wizard | Add to Person step | Create with MD → shows
E012 | MEDIUM | TermGap | StaffDirectory | No bulk import/batch creation | No CSV import capability | Build BulkImport component | Upload CSV → all created
E013 | MEDIUM | TermGap | StaffDirectory | No user comparison/diff tool | Can't compare two users | Add Compare action | Side-by-side diff shown
E014 | LOW | TermGap | StaffForm | No delegation of authority workflow | Cosigner is just text, no real workflow | Searchable provider lookup | Select from provider list
E015 | LOW | TermGap | StaffDirectory | No user template/profile feature | Can't save template users | Allow marking templates | Create from template

## 06-UX
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
F001 | HIGH | UX | StaffForm | Name is one field requiring LAST,FIRST format | Users must type VistA format | Separate: Last, First, MI fields | 3 fields → VistA format on submit
F002 | HIGH | UX | StaffDirectory | Titles blank for most users | VistA field 8 rarely populated | Derive from role → keys → fallback | Title always populated
F003 | HIGH | UX | StaffDirectory | Staff ID (S-DUZ) meaningless | DUZ has no business meaning | Prioritize Employee ID | Employee ID shown first
F004 | MEDIUM | UX | StaffDirectory | KPI cards generic | Total/Active/E-Sig/Locked not ideal | Replace E-Sig with Providers count | Better metrics shown
F005 | MEDIUM | UX | StaffForm | No password strength indicator | No visual feedback on strength | Add meter: Weak/Fair/Strong | Strength shown visually
F006 | MEDIUM | UX | StaffForm | No password show/hide toggle | Can't verify typed password | Add eye icon toggle | Click → password visible
F007 | MEDIUM | UX | StaffForm | No username uniqueness check | Conflict found only on submit | On blur check availability | Shows ✓Available or ✗Taken
F008 | MEDIUM | UX | StaffForm | DOB allows future dates | No max attribute | Set max=today, show age | Future blocked, age shown
F009 | MEDIUM | UX | StaffForm | No unsaved changes warning | Close tab = data lost | beforeunload + router blocker | Dialog on navigate away
F010 | MEDIUM | UX | StaffForm | Cosigner is free text | No provider validation | Searchable provider dropdown | Select from provider list
F011 | MEDIUM | UX | StaffForm | Can't jump to wizard steps | Must go sequentially | Make completed labels clickable | Click step 1 from step 3
F012 | MEDIUM | UX | StaffForm | No real-time validation on blur | Errors only on Next click | onBlur validation per field | Leave empty → instant error
F013 | MEDIUM | UX | StaffForm | No DEA format validation | No check (should be 2 letters+7 digits) | Validate regex pattern | Invalid DEA → error
F014 | MEDIUM | UX | StaffDirectory | No inline edit for basic fields | Phone/email need full wizard | Add EditableDetailField for basic fields | Click phone → edit inline
F015 | MEDIUM | UX | StaffDirectory | Access letter bare-bones | No branding/role/permissions | Full letter with org, role, all data | Professional letter printed
F016 | MEDIUM | UX | StaffDirectory | Filters not in URL params | Refresh = filters lost | useSearchParams sync | Refresh preserves filters
F017 | MEDIUM | UX | StaffDirectory | No search debounce | Every keystroke re-filters | 200ms debounce | No input lag
F018 | MEDIUM | UX | StaffDirectory | No sort by recently created | Can't find new users | Add sort options | Recent users at top
F019 | MEDIUM | UX | StaffDirectory | No role-source indicator | Can't tell role vs individual keys | Badge: "From: Physician" | Source shown per key
F020 | MEDIUM | UX | StaffForm | Review step no diff | No change highlighting | Color-code changes | Changed fields highlighted
F021 | MEDIUM | UX | StaffDirectory | Multi-division minimal display | Just comma-separated string | Individual badges, add/remove | Badges with station codes
F022 | MEDIUM | UX | StaffDirectory | No impact warning on key removal | Generic confirm only | Show KEY_IMPACTS text | Impact description in confirm
F023 | MEDIUM | UX | StaffDirectory | Deactivation reasons from VistA | Our invention, not terminal | Keep but document as enhancement | Reason stored in field 9.4
F024 | LOW | UX | StaffDirectory | No pinned/favorite staff | Admin can't bookmark users | Star icon, pinned section | Pinned users at top
F025 | LOW | UX | StaffDirectory | No recent activity feed | No per-user change history | Show last 5 audit entries | Detail shows recent changes
F026 | LOW | UX | StaffDirectory | No keyboard shortcuts | No Ctrl+N, Ctrl+F | Add shortcuts with hints | Ctrl+N → new wizard
F027 | LOW | UX | Global | No dark mode | Fixed light theme | CSS variable dark mode toggle | Dark mode renders correctly
F028 | LOW | UX | StaffForm | No responsive/mobile wizard | May break on narrow screens | Responsive breakpoints | Tablet renders correctly

## 07-Security
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
G001 | HIGH | Security | LoginPage | No login rate limiting | Brute-force possible | Rate limit 5/min per IP | 6th attempt blocked
G002 | HIGH | Security | api.js | Session in sessionStorage — XSS risk | JS can steal token | httpOnly cookie instead | Token not in JS
G003 | HIGH | Security | ZVEADMIN.m | Full SSN in API response | DETAIL returns full SSN | Mask to last 4 on server | API shows ***-**-1234
G004 | MEDIUM | Security | server.mjs | No CSRF protection | No CSRF token | Add per-session CSRF token | Request without token → 403
G005 | MEDIUM | Security | ZVEADMN1.m | No audit for key assignment | KEYASSN has no AUDITLOG | Add AUDITLOG call | Audit shows key assigned
G006 | MEDIUM | Security | ZVEADMN1.m | No audit for key removal | KEYREM has no AUDITLOG | Add AUDITLOG call | Audit shows key removed
G007 | MEDIUM | Security | server.mjs | No audit for clone | Clone untracked | Log source+new+keys | Audit shows clone details
G008 | MEDIUM | Security | StaffForm | No email validation | No regex check | Validate email format | Invalid → error
G009 | MEDIUM | Security | StaffForm | No phone validation | No format check | Validate 10 digits | Invalid → error
G010 | MEDIUM | Security | StaffForm | SSN last4 not validated | No 4-digit check | Validate /^\d{4}$/ | Invalid → error
G011 | MEDIUM | Security | StaffForm | Password rules inconsistent | Frontend vs Kernel mismatch | Align with VistA Kernel | Rules match VistA
G012 | LOW | Security | LoginPage | No remaining attempts display | User doesn't know lockout | Show X attempts remaining | Count shown on fail
G013 | LOW | Security | server.mjs | Provider edits not role-restricted | Any user can edit providers | Require XUMGR key | Non-admin → 403
G014 | LOW | Security | StaffDirectory | Access code in clone modal visible | Plain text input | Mask with show/hide toggle | Credentials masked

## 08-Perf
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
H001 | MEDIUM | Perf | StaffDirectory | No server-side pagination | All users loaded | Add ?page=N&limit=M | <1s with 1000 users
H002 | MEDIUM | Perf | StaffDirectory | E-sig separate API call | Could merge into LIST2 | Include in M routine | One call for all
H003 | MEDIUM | Perf | StaffDirectory | No hover prefetch for detail | Click→wait | Prefetch on hover | Instant detail
H004 | MEDIUM | Perf | RoleTemplates | Role assignment: N sequential calls | 6 keys = 6 calls | Batch RPC | One call for role
H005 | LOW | Perf | StaffForm | Ref data re-fetched on every open | Sites/depts/perms | Cache with TTL | Second open instant
H006 | LOW | Perf | StaffDirectory | No lazy load for detail sections | All sections at once | Load on expand | Basic info instant

## 09-Errors
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
I001 | MEDIUM | Error | StaffForm | VistA down mid-wizard: no recovery | Generic error, data lost | Show retry + auto-save | Progress saved
I002 | MEDIUM | Error | server.mjs | Create partial: no per-field report | User incomplete | Return per-field status | Warning for failed fields
I003 | MEDIUM | Error | RoleTemplates | Key assign errors not itemized | Generic error | Per-key results | Shows which failed
I004 | MEDIUM | Error | LoginPage | Login error same for all failures | Always "Invalid credentials" | Parse broker error | Distinct messages
I005 | MEDIUM | Error | StaffDirectory | Network error shows stale data | staffList not cleared | Clear on error + retry | Empty + retry button
I006 | LOW | Error | StaffForm | Submit error not scrolled to | May be off-screen | Scroll + toast | Error visible
I007 | LOW | Error | StaffDirectory | Clone error not specific | Generic message | Surface RPC error | Shows VistA message
I008 | LOW | Error | StaffDirectory | Deactivate error generic | No VistA reason | Surface M routine msg | Shows specific error

## 10-A11y
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
J001 | MEDIUM | A11y | StaffForm | No focus management on step change | Focus stays at top | Focus first field | Cursor in first input
J002 | MEDIUM | A11y | StaffDirectory | Color-only status indicators | Colorblind can't distinguish | Add text/icon | Status text visible
J003 | MEDIUM | A11y | Global | No aria-live for dynamic msgs | Screen reader misses | Add aria-live | Announced by SR
J004 | LOW | A11y | StaffDirectory | Modal focus trap missing | Tab escapes modal | Trap focus | Tab stays in modal
J005 | LOW | A11y | AppShell | No skip-to-content link | Must tab through nav | Add skip link | Link visible on Tab
J006 | LOW | A11y | DataTable | Rows not keyboard navigable | Can't arrow key | Arrow+Enter nav | Keyboard nav works

## 11-Terms
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
K001 | MEDIUM | Terms | Global | Staff ID vs Employee ID inconsistent | 3 different terms | Standardize | Consistent labels
K002 | MEDIUM | Terms | StaffDirectory | VistA key names still cryptic | PSDRPH, IBFIN shown raw | All 43 keys translated | Human names shown
K003 | MEDIUM | Terms | MailGroupMgmt | Mail group names are VistA jargon | IRM MAIL GROUP etc | Load description field | Descriptions shown
K004 | LOW | Terms | StaffForm | Access/Verify Code labels dated | Parenthetical jargon | Show Username/Password | Clean labels
K005 | LOW | Terms | server.mjs | DUZ in error messages | Meaningless to admin | Use user name | Name in errors
K006 | LOW | Terms | StaffDirectory | VistA file refs in tooltips | #200 confusing | Remove file numbers | User-friendly tooltips
K007 | LOW | Terms | StaffForm | Create vs Save vs Submit inconsistent | Different buttons | Create for new, Save for edit | Correct per mode
K008 | LOW | Terms | StaffDirectory | DISUSER/TERMDT in console logs | VistA internal | Human terms in logs | No jargon in logs

## 12-EdgeCases
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
L001 | MEDIUM | Edge | StaffForm | Apostrophe in name breaks VistA | O'BRIEN fails .01 transform | Sanitize or warn | Warning shown
L002 | MEDIUM | Edge | StaffForm | Very long names exceed 35-char limit | VistA max 35 | Char counter + enforce | 36 chars blocked
L003 | MEDIUM | Edge | server.mjs | Concurrent editing: no optimistic lock | Two admins overwrite | Version/timestamp check | Conflict detected
L004 | MEDIUM | Edge | StaffForm | Duplicate name error not clear | VistA error may be cryptic | Surface clear message | Shows "already exists"
L005 | LOW | Edge | StaffDirectory | Empty system: no onboarding msg | New install shows nothing | Welcome message | Helpful first-use msg
L006 | LOW | Edge | StaffDirectory | 50+ permissions overflow | Excessive scrolling | Collapse + "show more" | Shows 10 + expand
L007 | LOW | Edge | StaffForm | Session timeout mid-wizard | Data lost | Auto-save + re-auth | Progress restored
L008 | LOW | Edge | StaffDirectory | No-name record (corrupt .01) | Blank row | Show "(No Name #DUZ)" | Identified clearly

## 13-RoleAccuracy
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
M001 | HIGH | RoleAccuracy | RoleTemplates | Physician: 6 keys — Consider DG SENSITIVITY | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M002 | HIGH | RoleAccuracy | RoleTemplates | Nurse Practitioner: 5 keys — Consider GMRA ALLERGY VERIFY | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M003 | HIGH | RoleAccuracy | RoleTemplates | Physician Assistant: 4 keys — Missing ORCL-SIGN-NOTES | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M004 | HIGH | RoleAccuracy | RoleTemplates | Surgeon: 7 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M005 | HIGH | RoleAccuracy | RoleTemplates | Anesthesiologist: 5 keys — Consider PSB NURSE for med admin | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M006 | HIGH | RoleAccuracy | RoleTemplates | Registered Nurse: 5 keys — Consider GMRA ALLERGY VERIFY | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M007 | HIGH | RoleAccuracy | RoleTemplates | LPN: 4 keys — Consider if ORELSE needed | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M008 | HIGH | RoleAccuracy | RoleTemplates | Social Worker: 3 keys — Consider DG REGISTER | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M009 | HIGH | RoleAccuracy | RoleTemplates | Ward Clerk: 4 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M010 | HIGH | RoleAccuracy | RoleTemplates | Staff Pharmacist: 5 keys — Verify PSO MANAGER removed | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M011 | HIGH | RoleAccuracy | RoleTemplates | CS Pharmacist: 4 keys — Consider PSJ PHARMACIST | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M012 | HIGH | RoleAccuracy | RoleTemplates | Pharmacy Supervisor: 7 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M013 | HIGH | RoleAccuracy | RoleTemplates | Lab Technologist: 4 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M014 | HIGH | RoleAccuracy | RoleTemplates | Lab Supervisor: 5 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M015 | HIGH | RoleAccuracy | RoleTemplates | Phlebotomist: 3 keys — Consider LRCAP over LRLAB | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M016 | HIGH | RoleAccuracy | RoleTemplates | Rad Tech: 4 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M017 | HIGH | RoleAccuracy | RoleTemplates | Imaging Tech: 4 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M018 | HIGH | RoleAccuracy | RoleTemplates | Scheduling Clerk: 3 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M019 | HIGH | RoleAccuracy | RoleTemplates | Scheduling Supervisor: 5 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M020 | HIGH | RoleAccuracy | RoleTemplates | Registration Clerk: 5 keys — Verify DG REGISTRATION | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M021 | HIGH | RoleAccuracy | RoleTemplates | ADT Coordinator: 6 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M022 | HIGH | RoleAccuracy | RoleTemplates | ADT Supervisor: 5 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M023 | HIGH | RoleAccuracy | RoleTemplates | Billing Clerk: 3 keys — Verify IBFIN | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M024 | HIGH | RoleAccuracy | RoleTemplates | System Administrator: 5 keys — Verify XUAUDITING | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified
M025 | HIGH | RoleAccuracy | RoleTemplates | Chief of Staff: 6 keys — Complete | Verify all keys exist + clinical accuracy | M prompt: check each key. Review notes. | All keys verified

## 14-FieldAudit
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
N001 | MEDIUM | FieldAudit | StaffForm/Dir | Name .01: create=True edit=rename display=True valid=Partial | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Name .01 end-to-end
N002 | MEDIUM | FieldAudit | StaffForm/Dir | Sex 4: create=True edit=True display=True valid=Dropdown | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Sex 4 end-to-end
N003 | MEDIUM | FieldAudit | StaffForm/Dir | DOB 5: create=True edit=True display=True valid=Required | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace DOB 5 end-to-end
N004 | MEDIUM | FieldAudit | StaffForm/Dir | SSN 9: create=EXTRA edit=True display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace SSN 9 end-to-end
N005 | MEDIUM | FieldAudit | StaffForm/Dir | Access 2: create=True edit=True display=False valid=Min3 | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Access 2 end-to-end
N006 | MEDIUM | FieldAudit | StaffForm/Dir | Verify 11: create=True edit=True display=False valid=Min8 | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Verify 11 end-to-end
N007 | CRITICAL | FieldAudit | StaffForm/Dir | Email .151: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Email .151 end-to-end
N008 | CRITICAL | FieldAudit | StaffForm/Dir | Phone .132: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Phone .132 end-to-end
N009 | MEDIUM | FieldAudit | StaffForm/Dir | Title 8: create=True edit=True display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Title 8 end-to-end
N010 | MEDIUM | FieldAudit | StaffForm/Dir | Service 29: create=True edit=True display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Service 29 end-to-end
N011 | HIGH | FieldAudit | StaffForm/Dir | NPI 41.99: create=False edit=True display=True valid=10dig | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace NPI 41.99 end-to-end
N012 | HIGH | FieldAudit | StaffForm/Dir | DEA 53.2: create=False edit=True display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace DEA 53.2 end-to-end
N013 | HIGH | FieldAudit | StaffForm/Dir | ProvType 53.5: create=False edit=True display=True valid=Dropdown | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace ProvType 53.5 end-to-end
N014 | HIGH | FieldAudit | StaffForm/Dir | PersClass 53.1: create=False edit=Provider display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace PersClass 53.1 end-to-end
N015 | MEDIUM | FieldAudit | StaffForm/Dir | Menu 201: create=True edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Menu 201 end-to-end
N016 | HIGH | FieldAudit | StaffForm/Dir | Division 200.02: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Division 200.02 end-to-end
N017 | HIGH | FieldAudit | StaffForm/Dir | Language 200.07: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Language 200.07 end-to-end
N018 | HIGH | FieldAudit | StaffForm/Dir | VCNeverExp 9.5: create=False edit=False display=True valid=Toggle | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace VCNeverExp 9.5 end-to-end
N019 | HIGH | FieldAudit | StaffForm/Dir | Restrict 101.01: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Restrict 101.01 end-to-end
N020 | HIGH | FieldAudit | StaffForm/Dir | SigBlock 20.2/3: create=False edit=Provider display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace SigBlock 20.2/3 end-to-end
N021 | MEDIUM | FieldAudit | StaffForm/Dir | E-Sig 20.4: create=N/A edit=Clear display=True valid=N/A | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace E-Sig 20.4 end-to-end
N022 | HIGH | FieldAudit | StaffForm/Dir | Cosigner 53.42: create=False edit=False display=True valid=FreeText | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Cosigner 53.42 end-to-end
N023 | HIGH | FieldAudit | StaffForm/Dir | AuthMeds 53.11: create=False edit=Provider display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace AuthMeds 53.11 end-to-end
N024 | HIGH | FieldAudit | StaffForm/Dir | Degree 10.6: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Degree 10.6 end-to-end
N025 | HIGH | FieldAudit | StaffForm/Dir | TaxID 53.3: create=False edit=Provider display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace TaxID 53.3 end-to-end
N026 | HIGH | FieldAudit | StaffForm/Dir | FMAccess 3: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace FMAccess 3 end-to-end
N027 | HIGH | FieldAudit | StaffForm/Dir | OERR 200.0001: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace OERR 200.0001 end-to-end
N028 | HIGH | FieldAudit | StaffForm/Dir | Proxy 203.1: create=False edit=False display=True valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace Proxy 203.1 end-to-end
N029 | HIGH | FieldAudit | StaffForm/Dir | EmployeeID custom: create=False edit=False display=False valid=None | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace EmployeeID custom end-to-end
N030 | MEDIUM | FieldAudit | StaffForm/Dir | TermDate 9.2: create=DEACT edit=N/A display=True valid=N/A | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace TermDate 9.2 end-to-end
N031 | MEDIUM | FieldAudit | StaffForm/Dir | TermReason 9.4: create=Never edit=N/A display=True valid=N/A | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace TermReason 9.4 end-to-end
N032 | MEDIUM | FieldAudit | StaffForm/Dir | DISUSER n7: create=DEACT edit=N/A display=True valid=N/A | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace DISUSER n7 end-to-end
N033 | MEDIUM | FieldAudit | StaffForm/Dir | PwdChgDate 11.2: create=Never edit=N/A display=False valid=N/A | Per-field data flow check | Ensure field saves/loads/displays/validates | Trace PwdChgDate 11.2 end-to-end

## 15-ActionTraces
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
O001 | MEDIUM | ActionTrace | Various | Action: Create User — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Create User" → verify in VistA
O002 | MEDIUM | ActionTrace | Various | Action: Edit User — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Edit User" → verify in VistA
O003 | MEDIUM | ActionTrace | Various | Action: Deactivate — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Deactivate" → verify in VistA
O004 | MEDIUM | ActionTrace | Various | Action: Reactivate — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Reactivate" → verify in VistA
O005 | MEDIUM | ActionTrace | Various | Action: Unlock — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Unlock" → verify in VistA
O006 | MEDIUM | ActionTrace | Various | Action: Clone User — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Clone User" → verify in VistA
O007 | MEDIUM | ActionTrace | Various | Action: Clear E-Sig — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Clear E-Sig" → verify in VistA
O008 | MEDIUM | ActionTrace | Various | Action: Assign Permission — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Assign Permission" → verify in VistA
O009 | MEDIUM | ActionTrace | Various | Action: Remove Permission — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Remove Permission" → verify in VistA
O010 | MEDIUM | ActionTrace | Various | Action: Assign Role — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Assign Role" → verify in VistA
O011 | MEDIUM | ActionTrace | Various | Action: Edit Provider Field — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Edit Provider Field" → verify in VistA
O012 | MEDIUM | ActionTrace | Various | Action: Print Letter — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Print Letter" → verify in VistA
O013 | MEDIUM | ActionTrace | Various | Action: View Audit — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "View Audit" → verify in VistA
O014 | MEDIUM | ActionTrace | Various | Action: Search Staff — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Search Staff" → verify in VistA
O015 | MEDIUM | ActionTrace | Various | Action: Filter Status — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Filter Status" → verify in VistA
O016 | MEDIUM | ActionTrace | Various | Action: Filter Dept — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Filter Dept" → verify in VistA
O017 | MEDIUM | ActionTrace | Various | Action: Export CSV — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Export CSV" → verify in VistA
O018 | MEDIUM | ActionTrace | Various | Action: Load List — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Load List" → verify in VistA
O019 | MEDIUM | ActionTrace | Various | Action: Load Detail — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Load Detail" → verify in VistA
O020 | MEDIUM | ActionTrace | Various | Action: Login — end-to-end trace | Handler→service→route→RPC→M→response | Trace and verify each step | Perform "Login" → verify in VistA

## 16-Enhancements
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
P001 | LOW | Enhancement | Various | Enhancement: Photo/avatar upload | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P002 | LOW | Enhancement | Various | Enhancement: Quick-action hover toolbar | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P003 | LOW | Enhancement | Various | Enhancement: Status timeline | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P004 | LOW | Enhancement | Various | Enhancement: Permission diff on assign | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P005 | LOW | Enhancement | Various | Enhancement: Batch permission mgmt | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P006 | LOW | Enhancement | Various | Enhancement: Onboarding checklist | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P007 | LOW | Enhancement | Various | Enhancement: Credential delivery options | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P008 | LOW | Enhancement | Various | Enhancement: User groups/teams | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P009 | LOW | Enhancement | Various | Enhancement: Time-limited key access | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P010 | LOW | Enhancement | Various | Enhancement: Compliance dashboard | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P011 | LOW | Enhancement | Various | Enhancement: Advanced field:value search | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P012 | LOW | Enhancement | Various | Enhancement: Export profile as PDF | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P013 | LOW | Enhancement | Various | Enhancement: Scheduled deactivation | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P014 | LOW | Enhancement | Various | Enhancement: Periodic access review | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P015 | LOW | Enhancement | Various | Enhancement: Permission request workflow | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P016 | LOW | Enhancement | Various | Enhancement: Customizable detail layout | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P017 | LOW | Enhancement | Various | Enhancement: AD/LDAP import | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P018 | LOW | Enhancement | Various | Enhancement: Two-factor authentication | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P019 | LOW | Enhancement | Various | Enhancement: Per-field change audit | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P020 | LOW | Enhancement | Various | Enhancement: Smart role suggestions from title | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P021 | LOW | Enhancement | Various | Enhancement: Drag-drop role key editor | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P022 | LOW | Enhancement | Various | Enhancement: Dashboard widget for recent users | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P023 | LOW | Enhancement | Various | Enhancement: Auto-expire inactive accounts | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P024 | LOW | Enhancement | Various | Enhancement: Permission inheritance from department | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P025 | LOW | Enhancement | Various | Enhancement: Org chart visualization | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P026 | LOW | Enhancement | Various | Enhancement: Real-time user count badge | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P027 | LOW | Enhancement | Various | Enhancement: Session monitoring dashboard | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P028 | LOW | Enhancement | Various | Enhancement: Bulk deactivation with reason | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P029 | LOW | Enhancement | Various | Enhancement: Re-credential workflow | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end
P030 | LOW | Enhancement | Various | Enhancement: Mass division reassignment | Modern feature for competitive parity | Design, build, integrate with VistA | Feature works end-to-end

## 17-Ch2-Roles
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
R001 | HIGH | Ch2-Roles | RoleTemplates | Workspace grid not editable for custom roles | Display-only, can't change access levels | Make cells clickable: rw→ro→none. Save via updateCustomRole. | Click cell → cycles → saves
R002 | HIGH | Ch2-Roles | RoleTemplates | No Reset to Default for custom roles | Can't undo mistakes on cloned roles | Add button restoring original built-in key set | Reset → original keys restored
R003 | HIGH | Ch2-Roles | RoleTemplates | Built-in role edit shows no guidance | User may not know to clone first | Show: "Clone this role to customize" | Message appears for built-in
R004 | MEDIUM | Ch2-Roles | RoleTemplates | Role holder count is estimate, not exact | Intersection of key holders | Clarify in UI: "~12 staff (estimated)" | Shows approximate label
R005 | MEDIUM | Ch2-Roles | RoleTemplates | Staff tab doesn't show actual users | Shows count but may not list names | Load actual holders via ZVE KEY HOLDERS | Names listed
R006 | MEDIUM | Ch2-Roles | RoleTemplates | Custom role keys not grouped by department | Flat list of keys | Group by package/department like built-in roles | Grouped display
R007 | MEDIUM | Ch2-Roles | RoleTemplates | No export of role definition | Can't export role for documentation | Add "Export as JSON/CSV" | Role exported
R008 | MEDIUM | Ch2-Roles | RoleTemplates | No diff between two roles | Can't compare roles | Add Compare Roles feature | Side-by-side diff
R009 | MEDIUM | Ch2-Roles | RoleTemplates | Clone modal doesn't validate unique name | Can create duplicate-named custom roles | Check name uniqueness before create | Duplicate name → error
R010 | LOW | Ch2-Roles | RoleTemplates | No role usage statistics | Don't know which roles are most used | Track and display assignment count | Shows usage stats
R011 | HIGH | Ch2-Perms | PermsCatalog | Batch assign checks ORES/ORELSE but may miss on network error | try/catch around conflict check may skip | Ensure conflict check is mandatory | Conflict always checked
R012 | MEDIUM | Ch2-Perms | PermsCatalog | Standard vs Advanced mode switch unclear | User may not know about 689 keys | Better label: "Show all 689 keys" toggle | Clear toggle
R013 | MEDIUM | Ch2-Perms | PermsCatalog | No key category filter | Can't filter by Pharmacy/Lab/etc | Add category dropdown | Filter by package
R014 | MEDIUM | Ch2-Perms | PermsCatalog | No key dependency display | ORES needs PROVIDER but not shown | Show key dependencies | Shows: "ORES requires PROVIDER"
R015 | MEDIUM | Ch2-Perms | PermsCatalog | Holders list doesn't link to user detail | Names shown but not clickable | Make names clickable → navigate to user detail | Click name → user detail opens
R016 | MEDIUM | Ch2-Perms | PermsCatalog | No batch remove permission | Can only remove from one user at a time | Add batch remove like batch assign | Remove from multiple users
R017 | LOW | Ch2-Perms | PermsCatalog | No key search by "what can I do with this" | Must know key name or package | Task-based search: "prescribe" → ORES | Task search works
R018 | LOW | Ch2-Perms | PermsCatalog | No key history (who added/removed this key) | No per-key audit trail | Show assignment/removal history per key | History shown per key
R019 | LOW | Ch2-Perms | PermsCatalog | No "most commonly assigned keys" view | All keys equal weight | Sort by holder count desc | Popular keys at top
R020 | LOW | Ch2-Perms | PermsCatalog | Deep link from URL to specific key not supported | Can't share link to a key | URL param: /admin/permissions?key=ORES | Link opens to specific key

## 18-Ch3-SecConfig
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
S001 | HIGH | Ch3-Security | SecurityAuth | Login section 2P but non-login sections not — inconsistent | E-sig section has twoPersonRequired:false but is equally sensitive | Review which sections need 2P | Consistent 2P policy
S002 | MEDIUM | Ch3-Security | SecurityAuth | Session timeout slider has no live preview | User sets 900 but doesn't know that's 15 min | Show human-readable: "15 minutes" | Duration in human text
S003 | MEDIUM | Ch3-Security | SecurityAuth | Password expiration slider step size unclear | Slider 1-90 days but no tick marks | Add tick marks at 30/60/90 | Ticks visible
S004 | MEDIUM | Ch3-Security | SecurityAuth | Audit mode dropdown: "Audit All" vs "No Audit" risky | Accidental change to No Audit = compliance violation | Add confirmation for disabling audit | Confirm required for "No Audit"
S005 | MEDIUM | Ch3-Security | SecurityAuth | Pending 2P requests: no email notification to approver | Second admin must check page to see pending | Send email/MailMan to approving admin | Email sent on 2P submit
S006 | MEDIUM | Ch3-Security | SecurityAuth | Advanced section: IRM Mail Group is free text | Should be dropdown from actual mail groups | Dropdown populated from getMailGroups() | Select from list
S007 | MEDIUM | Ch3-Security | SecurityAuth | Change reason required but min length not enforced | Could type "x" as reason | Minimum 10 chars for change reason | Short reason rejected
S008 | LOW | Ch3-Security | SecurityAuth | E-sig policy section is all read-only — no action possible | User navigates here but can't do anything | Add note: "These are system-enforced policies" or remove section | Clear messaging
S009 | MEDIUM | Ch3-Config | SystemConfig | Most fields read-only — page feels useless | Only welcome msg and broker timeout editable | Add explanations of why read-only | Each field explains editability
S010 | MEDIUM | Ch3-Config | SystemConfig | Welcome message: no preview of how it looks on login | Edit textarea but can't see result | Add "Preview" button | Preview shows login screen
S011 | MEDIUM | Ch3-Config | SystemConfig | System info section: no refresh button | Data loaded once | Add manual refresh | Click refresh → updated info
S012 | MEDIUM | Ch3-Config | SystemConfig | Environment badge: sandbox vs production — no explanation | Just shows "Test/Sandbox" or "Production" | Add tooltip explaining implications | Tooltip explains
S013 | HIGH | Ch3-Params | SiteParameters | Module params: unlabeled fields show "Parameter #N" | DD FIELDS RPC may fail → generic labels | Better fallback: show field number + "Configure" hint | Clear label or explanation
S014 | MEDIUM | Ch3-Params | SiteParameters | Package params may show empty for uninitialized packages | Shows "This module uses default settings" | Add "Initialize" button or link to setup guide | Guidance provided
S015 | MEDIUM | Ch3-Params | SiteParameters | No search across all parameters | Must browse each module | Add cross-module search | Search "timeout" → finds across modules
S016 | MEDIUM | Ch3-Params | SiteParameters | Save button state unclear | May not show which fields changed | Highlight changed fields, show count | Changed fields highlighted
S017 | LOW | Ch3-Params | SiteParameters | No parameter history/changelog | Can't see what was changed when | Track param changes in audit log | History available per param
S018 | LOW | Ch3-Params | SiteParameters | No recommended values shown | User must know VHA guidelines | Show recommended range per param | Range shown

## 19-OtherPages
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
T001 | MEDIUM | Dashboard | AdminDashboard | Dashboard cards may show stale data | Loaded once, no auto-refresh | Add auto-refresh interval + manual refresh | Refresh updates counts
T002 | MEDIUM | Dashboard | AdminDashboard | No click-through from cards to filtered views | Click "Active Users: 45" but no navigation | Card click → filtered staff directory | Click → filtered view
T003 | LOW | Dashboard | AdminDashboard | No customizable widget layout | Fixed card arrangement | Drag-drop widget positioning | Customize layout
T004 | LOW | Dashboard | AdminDashboard | No trend data (users this week vs last) | Static counts only | Track over time, show trends | Sparkline charts
T005 | MEDIUM | Reports | AdminReports | Reports may timeout on large datasets | No loading timeout | Add timeout + partial results | Shows partial on timeout
T006 | MEDIUM | Reports | AdminReports | CSV export only — no PDF option | Text-only export | Add PDF export option | PDF downloaded
T007 | LOW | Reports | AdminReports | No scheduled/recurring reports | Must run manually each time | Add schedule: daily/weekly email | Report emailed on schedule
T008 | LOW | Reports | AdminReports | No custom report builder | Fixed report types | Allow field selection for custom reports | Custom report generated
T009 | HIGH | Alerts | AlertsNotify | MailMan messages: does send actually work? | sendMailManMessage calls ZVE MM SEND | Test: send message → verify in VistA MailMan | Message appears in VistA
T010 | HIGH | Alerts | AlertsNotify | MailMan delete: does it actually delete? | deleteMailManMessage calls ZVE MM DELETE | Test: delete → verify message gone in VistA | Message deleted from VistA
T011 | MEDIUM | Alerts | AlertsNotify | Alert create: does it work end-to-end? | createAlert calls ZVE ALERT CREATE | Test: create alert → verify in VistA | Alert created in VistA
T012 | MEDIUM | Alerts | AlertsNotify | No unread message count badge | Badge not shown anywhere | Add count to bell icon + page header | Unread count visible
T013 | LOW | Alerts | AlertsNotify | No message search | Must browse all messages | Add search across folders | Search finds messages
T014 | MEDIUM | Audit | AuditLog | Multiple audit sources may have inconsistent formats | FileMan audit vs signon log vs error log | Normalize display format | Consistent appearance
T015 | MEDIUM | Audit | AuditLog | No date range filter | Shows all entries | Add date picker range filter | Filter by date range
T016 | LOW | Audit | AuditLog | No export of audit data | View-only | Add CSV/PDF export | Audit exported
T017 | LOW | Audit | AuditLog | No alert on suspicious activity | No anomaly detection | Flag unusual patterns (mass key changes, off-hours access) | Suspicious entries highlighted
T018 | MEDIUM | Clinics | ClinicMgmt | Clinic create: does it write to File 44? | createClinic calls ZVE CLNM ADD | Test: create → verify in VistA File 44 | Clinic in File 44
T019 | MEDIUM | Clinics | ClinicMgmt | Clinic edit: does field update save? | updateClinicField → DDR FILER | Test: edit name → verify in VistA | Name updated
T020 | MEDIUM | Clinics | ClinicMgmt | Clinic inactivate: does it set correct field? | May have same field-number bug as user DEACT | Verify correct File 44 field for inactive status | Status changes in VistA
T021 | LOW | Clinics | ClinicMgmt | No clinic availability calendar view | Grid may show but not editable | Add calendar UI for slot management | Calendar shows availability
T022 | MEDIUM | Wards | WardMgmt | Ward edit: does it save to File 42? | ZVE WRDM EDIT writes to File 42 | Test: edit → verify in VistA | Ward updated in VistA
T023 | MEDIUM | Wards | WardMgmt | Ward bed count: is it live from VistA? | May be static | Verify real-time bed data | Bed count matches VistA
T024 | LOW | Wards | WardMgmt | No ward-to-department mapping visible | Relationship not shown | Show department association | Department shown per ward
T025 | MEDIUM | Devices | DeviceMgmt | Device delete: does it remove from File 3.5? | deleteDevice → DDR FILER | Test: delete → verify gone from VistA | Device removed
T026 | MEDIUM | Devices | DeviceMgmt | Test print: does it actually send to device? | testPrintDevice calls ZVE DEV TESTPRINT | Test: print → verify output | Print job sent
T027 | LOW | Devices | DeviceMgmt | No device status monitoring | Static list only | Add live status check (online/offline) | Status shown per device
T028 | MEDIUM | MailGroups | MailGrpMgmt | Add member: does it actually add to VistA? | addMailGroupMember → ZVE MAILGRP ADD | Test: add member → verify in VistA File 3.8 | Member in group
T029 | MEDIUM | MailGroups | MailGrpMgmt | Remove member: does it actually remove? | handleRemoveMember → ZVE MAILGRP REMOVE | Test: remove → verify gone from VistA | Member removed
T030 | MEDIUM | MailGroups | MailGrpMgmt | Group descriptions not shown | Names only, no context | Load description field from File 3.8 | Descriptions visible
T031 | LOW | MailGroups | MailGrpMgmt | No group creation from UI | Can only manage existing groups | Add create group functionality | New group created
T032 | MEDIUM | Depts | DeptService | Department create: does it write to File 49? | handleCreate → ??? | Verify creates in VistA File 49 | Dept in VistA
T033 | MEDIUM | Depts | DeptService | Department delete: safety check? | handleDeleteDept — does it check for assigned users? | Block delete if users assigned to department | Warning if users assigned
T034 | LOW | Depts | DeptService | No department hierarchy visualization | Flat list | Add tree/org-chart view | Hierarchy visible
T035 | MEDIUM | Sites | SiteMgmt | Workspace toggles: do they save to VistA? | ZVE SITE WS SET called | Test: toggle → verify in VistA | Toggle persists
T036 | MEDIUM | Sites | SiteMgmt | Site delete: what happens to assigned users? | handleDeleteSite — no user check | Block delete if users assigned | Warning if users exist
T037 | LOW | Sites | SiteMgmt | No site comparison view | Can't compare two divisions | Add Compare Sites | Side-by-side shown
T038 | MEDIUM | Health | SystemHealth | HL7 shutdown: does it actually stop the interface? | shutdownHL7Interface → ZVE HL7 actions | Test: shutdown → verify interface stopped | Interface stopped in VistA
T039 | MEDIUM | Health | SystemHealth | HL7 enable: does it restart? | enableHL7Interface → ZVE HL7 | Test: enable → verify running | Interface running
T040 | MEDIUM | Health | SystemHealth | TaskMan status: is it live? | getTaskManStatus → ZVE TASKMAN STATUS | Verify real-time status | Status matches VistA
T041 | LOW | Health | SystemHealth | No historical uptime tracking | Point-in-time only | Track and display uptime percentage | Uptime shown
T042 | LOW | Health | SystemHealth | No alert thresholds for health metrics | No auto-notification when unhealthy | Set thresholds, send alerts | Alert on threshold breach

## 20-Global
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
X001 | HIGH | Global | AppShell | No global error boundary | Unhandled JS error = white screen | Add React ErrorBoundary | Error → fallback UI
X002 | HIGH | Global | api.js | API timeout not configurable | Hard-coded or browser default | Add configurable timeout (30s default) | Slow response → timeout error
X003 | MEDIUM | Global | NavRail | Active nav item not highlighted on sub-routes | Click Staff Directory → Admin highlighted but sub-nav may not | Verify active state on all sub-routes | Correct item highlighted
X004 | MEDIUM | Global | AppShell | No breadcrumb navigation | Breadcrumb prop exists but may not be consistent | Ensure every page passes correct breadcrumb | Breadcrumbs show path
X005 | MEDIUM | Global | api.js | 401 redirect may lose current page context | Expired session → login → redirects to dashboard not original page | Store intended URL, redirect after login | Returns to original page
X006 | MEDIUM | Global | Global | No loading state consistency | Some pages show skeleton, others spinner, others nothing | Standardize: skeleton for pages, spinner for actions | Consistent loading UX
X007 | MEDIUM | Global | Global | No success toast consistency | Some show banner, others inline, others nothing | Standardize success feedback | Consistent success UX
X008 | MEDIUM | Global | Global | No confirmation dialog consistency | Some use ConfirmDialog, others window.confirm (should be 0) | All confirmations via ConfirmDialog | No window.confirm
X009 | LOW | Global | Global | No print stylesheet | Ctrl+P prints nav and shell | Add @media print to hide shell | Print shows content only
X010 | LOW | Global | Global | No favicon or page title management | Tab shows generic title | Set page-specific titles | Tabs show page names
X011 | LOW | Global | Global | No feature flags system | Can't enable/disable features per tenant | Add feature flag infrastructure | Features toggleable
X012 | LOW | Global | Global | No telemetry/analytics hooks | No usage tracking | Add event tracking infrastructure | Usage data collected
X013 | LOW | Global | Global | No i18n framework | English only | Add react-intl or similar | Ready for translation
X014 | LOW | Global | Global | No help/documentation links | No in-app help | Add ? icon linking to docs per page | Help links to relevant docs
X015 | LOW | Global | Global | No changelog/release notes page | Users don't know what changed | Add /admin/changelog page | Changelog visible
X016 | LOW | Global | DataTable | Column visibility toggle missing | Can't hide/show columns | Add column picker dropdown | Toggle columns
X017 | LOW | Global | DataTable | No row count display | Don't know total results | Show "Showing 1-25 of 342" | Count displayed
X018 | LOW | Global | DataTable | No density toggle (compact/comfortable) | Fixed row height | Add density switch | Rows more compact
X019 | LOW | Global | SharedComps | ConfirmDialog: no keyboard shortcut | Must click buttons | Enter=confirm, Escape=cancel | Keyboard works
X020 | LOW | Global | SharedComps | FilterChips: no "Clear All" button | Must remove one by one | Add "Clear All Filters" link | One click clears all

## 21-Workflow
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
W001 | MEDIUM | Workflow | StaffDirectory | Create non-provider: verify 3 steps actually work | Provider step must auto-skip | Test with Scheduling Clerk role | 3 steps shown, not 4
W002 | MEDIUM | Workflow | StaffDirectory | Create provider: verify 4 steps all save | Every field must reach VistA | Test with Physician role | All data in VistA
W003 | MEDIUM | Workflow | StaffDirectory | Edit single field: too many clicks | Full wizard for one field change | Inline edit for common fields | 1-click edit for phone
W004 | MEDIUM | Workflow | StaffDirectory | Deactivate: 4 clicks → can be 3 | Combine reason + confirm | Single dialog with reason + confirm | 3-click deactivate
W005 | MEDIUM | Workflow | RoleTemplates | Assign role from directory: 5+ clicks | Open detail→Assign Role→search→select→confirm | Quick-assign dropdown in detail | 3-click assign
W006 | LOW | Workflow | StaffDirectory | Find user in 500+ list: slow client filter | No server-side search | Use server search for >200 users | <200ms even with 1000
W007 | LOW | Workflow | StaffForm | Bulk onboard: 1 user at a time | No CSV import | Add CSV bulk import | 10 users via CSV
W008 | LOW | Workflow | StaffDirectory | View by role: no filter | Can't filter to "all physicians" | Add role filter | Shows role members
W009 | LOW | Workflow | StaffDirectory | Reset all perms: 1 at a time | Tedious with 20+ keys | Add "Remove All" action | All keys removed
W010 | LOW | Workflow | StaffDirectory | No recently viewed users | Can't quickly re-access | Track and show recent views | Recent users accessible

## 22-API
ID | Sev | Cat | Page | Summary | Detail | Fix | Verify
Y001 | HIGH | API | server.mjs | GET /users: keyCount returned but not prominent | In response but not shown as column | Add Keys column to table | Key count visible
Y002 | HIGH | API | server.mjs | GET /users: isProvider not used for table badge | In response, used for KPI only | Add provider badge in table | Provider badge visible
Y003 | MEDIUM | API | server.mjs | POST /users: no full user in response | Must re-fetch after create | Return full user detail | Create returns full data
Y004 | MEDIUM | API | server.mjs | PUT /users: no stored value in response | Returns input, not canonical value | Return VistA-stored value | Response shows stored value
Y005 | MEDIUM | API | server.mjs | DELETE key: keyId format ambiguous | IEN or name? | Document: always use key name | Consistent key ID format
Y006 | MEDIUM | API | server.mjs | GET /esig-status: different ID format | Uses {id,duz} vs {ien} | Standardize to duz everywhere | Consistent ID field
Y007 | LOW | API | server.mjs | No pagination on GET /users | All users returned | Add ?page=N&limit=M | Paginated response
Y008 | LOW | API | server.mjs | No ETag/caching headers | Browser can't cache | Add ETag support | 304 on no-change
Y009 | LOW | API | server.mjs | Error format inconsistent | Some {error}, some {msg} | Standardize {ok,error,code} | All errors same shape
Y010 | LOW | API | server.mjs | No API docs / OpenAPI spec | No machine-readable docs | Generate OpenAPI spec | Swagger docs available